## V7.0.9
|  |  | Customer : | Zound
Project Name | Hendrix M Lite V3 | FW TL | Nick Wang
Version # | 7.0.9 | Release Date | 2022-05-25
CheckSum | D:\Projects\&Zound\Hendrix_M_Lite\New folder\Hendrix_M_Lite_GD\sw\project_files\Hendrix_M\Release\Hendrix_LiteV3_Notes | SHA1-ID | 02ce270129dcf53efa36594362aa68e820705143
Release Package Path | file://doc/Tymphany/SE%20SW%20Releases/Releases/Zound/Hendrix_M_Lite_V3/
Description | FW release for Hendrix Lite
Release Package | 1. MCU [Contains mcu image] 2. BT [Contains Bluetooth module image] 3. DSP [Contains the DSP design]
Release Contents | 1. MCU Firmware: 7.0.9 2. BT Firmware: 7.0.9 3. ADAU1761 : 0.6 EQ 3.10
Major Modifications Included in this release | [MCU] 1. Version number forward with the BT FW. [BT] 1. Resolve the case #2 of the BRH-24.
Special Notes
Bug Fix | BRH-24 case #2
Known Issues

## V7.0.8
|  |  | Customer : | Zound
Project Name | Hendrix M Lite V3 | FW TL | Nick Wang
Version # | 7.0.8 | Release Date | 2022-05-22
CheckSum | D:\Projects\&Zound\Hendrix_M_Lite\New folder\Hendrix_M_Lite_GD\sw\project_files\Hendrix_M\Release\Hendrix_LiteV3_Notes | SHA1-ID | 02ce270129dcf53efa36594362aa68e820705143
Release Package Path | file://doc/Tymphany/SE%20SW%20Releases/Releases/Zound/Hendrix_M_Lite_V3/
Description | FW release for Hendrix Lite
Release Package | 1. MCU [Contains mcu image] 2. BT [Contains Bluetooth module image] 3. DSP [Contains the DSP design]
Release Contents | 1. MCU Firmware: 7.0.8 2. BT Firmware: 7.0.8 3. ADAU1761 : 0.6 EQ 3.10
Major Modifications Included in this release | [MCU] 1. Configure I2C pins to low in standby mode by EE's suggestion [BT] 1. Resolve the BRH-24, 35
Special Notes
Bug Fix | BRH-24, 35
Known Issues

## V7.0.7
|  |  | Customer : | Zound
Project Name | Hendrix M Lite V3 | FW TL | Nick Wang
Version # | 7.0.7 | Release Date | 2022-05-18
CheckSum | D:\Projects\&Zound\Hendrix_M_Lite\New folder\Hendrix_M_Lite_GD\sw\project_files\Hendrix_M\Release\Hendrix_LiteV3_Notes | SHA1-ID | 02ce270129dcf53efa36594362aa68e820705143
Release Package Path | file://doc/Tymphany/SE%20SW%20Releases/Releases/Zound/Hendrix_M_Lite_V3/
Description | FW release for Hendrix Lite
Release Package | 1. MCU [Contains mcu image] 2. BT [Contains Bluetooth module image] 3. DSP [Contains the DSP design]
Release Contents | 1. MCU Firmware: 7.0.7 2. BT Firmware: 7.0.7 3. ADAU1761 : 0.6 EQ 3.10
Major Modifications Included in this release | [MCU] 1. Resolve the BRH-11. [BT] 1. Modify AVCTP to v1.4 for certification.
Special Notes
Bug Fix | BRH-11
Known Issues

## V7.0.6
|  |  | Customer : | Zound
Project Name | Hendrix M Lite V3 | FW TL | Nick Wang
Version # | 7.0.6 | Release Date | 2022-05-13
CheckSum | D:\Projects\&Zound\Hendrix_M_Lite\New folder\Hendrix_M_Lite_GD\sw\project_files\Hendrix_M\Release\Hendrix_LiteV3_Notes | SHA1-ID | 02ce270129dcf53efa36594362aa68e820705143
Release Package Path | file://doc/Tymphany/SE%20SW%20Releases/Releases/Zound/Hendrix_M_Lite_V3/
Description | FW release for Hendrix Lite
Release Package | 1. MCU [Contains mcu image] 2. BT [Contains Bluetooth module image] 3. DSP [Contains the DSP design]
Release Contents | 1. MCU Firmware: 7.0.6 2. BT Firmware: 7.0.6 3. ADAU1761 : 0.6 EQ 3.10
Major Modifications Included in this release | [MCU] 1. Improve the audio cue related algorithm. 2. Re-define the pulse duration from the BT module to make the communication robust. [BT] 1. Follows Joplin's reconnect algorithm to improve the reconnection feature. 2. Re-define the pulse duration sending to MCU to make the communication robust.
Special Notes
Bug Fix | BRH-3, 8, 14, 18, 22, 24, 25, 27, 28, 29, 32, 33
Known Issues | BRH-11, still on going

## V7.0.5
|  |  | Customer : | Zound
Project Name | Hendrix M Lite V3 | FW TL | Nick Wang
Version # | 7.0.5 | Release Date | 2022-04-29
CheckSum | D:\Projects\&Zound\Hendrix_M_Lite\New folder\Hendrix_M_Lite_GD\sw\project_files\Hendrix_M\Release\Hendrix_LiteV3_Notes | SHA1-ID | 02ce270129dcf53efa36594362aa68e820705143
Release Package Path | file://doc/Tymphany/SE%20SW%20Releases/Releases/Zound/Hendrix_M_Lite_V3/
Description | FW release for Hendrix Lite
Release Package | 1. MCU [Contains mcu image] 2. BT [Contains Bluetooth module image] 3. DSP [Contains the DSP design]
Release Contents | 1. MCU Firmware: 7.0.5 2. BT Firmware: 7.0.5 3. ADAU1761 : 0.6 EQ 3.10
Major Modifications Included in this release | [MCU] 1. Modify the mute/unmute timimg control to play audio cue without corruption. [BT] 1. Resolce the re-connection issue due to the conflic between single-point and multi-point. 2. Correct the UI. Cancel the link loss timeout indication tone. 3. Fix the multi-point behavior.
Special Notes
Bug Fix | BRH-3, 4, 8, 14, 18, 20, 22, 24, 25, 26
Known Issues | AG 1 and 2 paired. AG1 is streamimg, AG2 reconnect but no reconnection tone.

## V7.0.4
|  |  | Customer : | Zound
Project Name | Hendrix M Lite V3 | FW TL | Nick Wang
Version # | 7.0.4 | Release Date | 2022-04-15
CheckSum | D:\Projects\&Zound\Hendrix_M_Lite\New folder\Hendrix_M_Lite_GD\sw\project_files\Hendrix_M\Release\Hendrix_LiteV3_Notes | SHA1-ID | 9f1588fd2f4996f20f3869cbfc84d271
Release Package Path | file://doc/Tymphany/SE%20SW%20Releases/Releases/Zound/Hendrix_M_Lite_V3/
Description | FW release for Hendrix Lite
Release Package | 1. MCU [Contains mcu image] 2. BT [Contains Bluetooth module image] 3. DSP [Contains the DSP design]
Release Contents | 1. MCU Firmware: 7.0.4 2. BT Firmware: 7.0.4 3. ADAU1761 : 0.6 EQ 3.10
Major Modifications Included in this release | [MCU] 1. Resolve the indication of cancel pairing during charging issue. (BRH-13) [BT] 1. Resolve the reconnection issue. The BT module cannot wake up correctly after going to standby or power up with charging core plugged-in. (BRH-15, 16, 17) 2. Correct multipoint indication and audio cue handling. (BRH-12) 3. Resolve cannot store 8 paired phones in PDL issue. (BRH-18)
Special Notes
Bug Fix | Cancel pairing indications (BRH-13)
Multipoint handling related (BRH- 12)
Recoonection issues (BRH-15, 16, 17)
Cannot store 8 paired phones (BRH-18)
Known Issues | BRH-14 has not been resolved. It still occurs sometimes.

## V7.0.3
|  |  | Customer : | Zound
Project Name | Hendrix M Lite V3 | FW TL | Nick Wang
Version # | 7.0.3 | Release Date | 2022-03-31
CheckSum | D:\Projects\&Zound\Hendrix_M_Lite\New folder\Hendrix_M_Lite_GD\sw\project_files\Hendrix_M\Release\Hendrix_LiteV3_Notes | SHA1-ID | 3e1e7f9eaea33b9b1dfbdbfc6b54d95a
Release Package Path | file://doc/Tymphany/SE%20SW%20Releases/Releases/Zound/Hendrix_M_Lite_V3/
Description | FW release for Hendrix Lite
Release Package | 1. MCU [Contains mcu image] 2. BT [Contains Bluetooth module image] 3. DSP [Contains the DSP design]
Release Contents | 1. MCU Firmware: 7.0.3 2. BT Firmware: 7.0.3 3. ADAU1761 : 0.6 EQ 3.10
Major Modifications Included in this release | [MCU] 1. Fine tune the handshaking signal with the BT module. [BT] 1. Correct BT output gain. (BRH-6) 2. Fine tune the handshaking signal with the MCU. 3. Follow original process to play audio cues. Resolve the cue truncated issue, cue volume not correct. (ZSR-55) (BRH-5) 4. Resolve the reconnecting failed issue. (ZSR-54) 5. Charging tone play correctly.
Special Notes
Bug Fix | Audio cue related issue. (ZSR-55) (BRH-5)
Btoutput gain issue. (BRH-6)
Reconnection issue. (ZSR-54) (BRH-4)
Known Issues | Some interactions seem not correct during charging. Need to be further checked.

## V7.0.2
|  |  | Customer : | Zound
Project Name | Hendrix M Lite V3 | FW TL | Nick Wang
Version # | 7.0.2 | Release Date | 2022-03-17
CheckSum | D:\Projects\&Zound\Hendrix_M_Lite\New folder\Hendrix_M_Lite_GD\sw\project_files\Hendrix_M\Release\Hendrix_LiteV3_Notes | SHA1-ID
Release Package Path | file://doc/Tymphany/SE%20SW%20Releases/Releases/Zound/Hendrix_M_Lite_V3/
Description | FW release for Hendrix Lite
Release Package | 1. MCU [Contains mcu image] 2. BT [Contains Bluetooth module image] 3. DSP [Contains the DSP design]
Release Contents | 1. MCU Firmware: 7.0.2 2. BT Firmware: 7.0.2 3. ADAU1761 : 0.6 EQ 3.10
Major Modifications Included in this release | [MCU] 1. Modify the power up sequence to enable the BT module correctly [BT] 1. Facory reset feature correct. PDL cleared after factory reset. 2. Improved the reconnect and linkloss reconnect.
Special Notes
Bug Fix | BT not enabled correctly in 7.0.1. (BRH-2)
BT PDL not cleared after facory reset.
Known Issues | BT module ooutput gain incorrect. Louder about 6dB than MP version.
Charging tone missed or incorrect sometimes.

## V7.0.1
|  |  | Customer : | Zound
Project Name | Hendrix M Lite V3 | FW TL | Nick Wang
Version # | 7.0.1 | Release Date | 2022-02-24
CheckSum | D:\Projects\&Zound\Hendrix_M_Lite\New folder\Hendrix_M_Lite_GD\sw\project_files\Hendrix_M\Release\Hendrix_LiteV3_Notes | SHA1-ID
Release Package Path | file://doc/Tymphany/SE%20SW%20Releases/Releases/Zound/Hendrix_M_Lite_V3/
Description | FW release for Hendrix Lite
Release Package | 1. MCU [Contains mcu image] 2. BT [Contains Bluetooth module image] 3. DSP [Contains the DSP design]
Release Contents | 1. MCU Firmware: 7.0.1 2. BT Firmware: 7.0.1 3. ADAU1761 : 0.6 EQ 3.10
Major Modifications Included in this release | [MCU] 1. Modify the power up sequence to enable the BT module 2. Reolve the abnormal reboot after powering down [BT] 1. Add 1K tone for production line test 2. Correct all the audio cues based on the UI spec 3. Solve the multipoint reconnection issue 4. OTA feature enable
Special Notes
Bug Fix
Known Issues | Charging tone missing when device connects to the power. Should be fixed next release.
BT PDL not cleared after facory reset. Should be fixed in next release.
Audio gain is not correct due to new amplifiers RT9120S and AD52090 are used in V3. Still under tuning.

## V7.0.0
|  |  | Customer : | Zound
Project Name | Hendrix M Lite V3 | FW TL | Nick Wang
Version # | 7.0.0 | Release Date | 2022-02-17
CheckSum | D:\Projects\&Zound\Hendrix_M_Lite\New folder\Hendrix_M_Lite_GD\sw\project_files\Hendrix_M\Release\Hendrix_LiteV3_Notes | SHA1-ID | 6f4f116c5e4f74f15a44a2666f56432dc6c7a051
Release Package Path | file://doc/Tymphany/SE%20SW%20Releases/Releases/Zound/Hendrix_M_Lite_V3/
Description | FW release for Hendrix Lite
Release Package | 1. MCU [Contains mcu image] 2. DSP [Contains the DSP design]
Release Contents | 1. MCU Firmware :7.0.0 + ADAU1761 : 0.6 EQ 3.10
Major Modifications Included in this release | Increase I2C clock time from 100K to 400K Bug Fix: Audio driver change due to digital amp and analog amp change. For V3 PCBA.
Special Notes
Bug Fix

## V6.0.7
|  |  | Customer : | Zound
Project Name | Hendrix M Lite V2 | FW TL | Edmond Sung
Version # | 6.0.7 | Release Date | 2021-09-03
CheckSum | D:\Projects\&Zound\Hendrix_M_Lite\New folder\Hendrix_M_Lite_GD\sw\project_files\Hendrix_M\Release\Hendrix_LiteV2_Notes | SHA1-ID | 83686174e9f8329dea4621b01c58afd634994e17
Release Package Path | http://intranet.tymphany.com/Departments/sw/Shared%20Documents/Forms/AllItems.aspx?RootFolder=%2FDepartments%2Fsw%2FShared%20Documents%2FSW%20Releases%2FReleases%2FZound%2FHendrix%5FM%5FLite%5FV2%2F6%2E0%2E7&FolderCTID=0x0120000760EF0E9D65B249BB00FD8C55A72E1B&View=%7BA4ACADA0%2D4A0A%2D47E6%2D8D6F%2D71FEB1C552CB%7D&InitialTabId=Ribbon%2EDocument&VisibilityContext=WSSTabPersistence
Description | FW release for Hendrix Lite
Release Package | 1. BT [Contains Bluetooth module image] 2. MCU [Contains mcu image] 3. DSP [Contains the DSP design]
Release Contents | 1. MCU Firmware :6.0.7 + ADAU1761 : 0.6 EQ 3.10 + BT QCC3008 : ZoundHendrix_M_FW_201812201739
Major Modifications Included in this release | Increase I2C clock time from 100K to 400K Bug Fix: Improve power on time. ZSR-43 The GD version DUT startup speed is obviously slower than ST version DUT
Special Notes
Bug Fix

## V6.0.6
|  |  | Customer : | Zound
Project Name | Hendrix M Lite V2 | FW TL | Edmond Sung
Version # | 6.0.6 | Release Date | 2021-08-27
CheckSum |  | SHA1-ID
Release Package Path | http://intranet.tymphany.com/Departments/sw/Shared%20Documents/Forms/AllItems.aspx?RootFolder=%2FDepartments%2Fsw%2FShared%20Documents%2FSW%20Releases%2FReleases%2FZound%2FHendrix%5FM%5FLite%5FV2&FolderCTID=0x0120000760EF0E9D65B249BB00FD8C55A72E1B&View=%7BA4ACADA0%2D4A0A%2D47E6%2D8D6F%2D71FEB1C552CB%7D
Description | FW release for Hendrix Lite
Release Package | 1. BT [Contains Bluetooth module image] 2. MCU [Contains mcu image] 3. DSP [Contains the DSP design]
Release Contents | 1. MCU Firmware :6.0.6 + ADAU1761 : 0.6 EQ 3.10 + BT QCC3008 : ZoundHendrix_M_FW_201812201739
Major Modifications Included in this release | Bug Fix: ZSR-40 Charging mode and Long-playing APTX ZSR-39 Unknown situation crash ZSR-32 When playing music, leaving the Bluetooth range, after 12 hours, the machine crashes, and there is no response when checking the power cord ZSR-30 Unknown situation crash,Did not enter standby mode for 10 minutes
Special Notes
Bug Fix

## V6.0.5
|  |  | Customer : | Zound
Project Name | Hendrix M Lite V2 | FW TL | Edmond Sung
Version # | 6.0.5 | Release Date | 2021-08-03
CheckSum |  | SHA1-ID
Release Package Path | http://intranet.tymphany.com/Departments/sw/Shared%20Documents/Forms/AllItems.aspx?RootFolder=%2FDepartments%2Fsw%2FShared%20Documents%2FSW%20Releases%2FReleases%2FZound%2FHendrix%5FM%5FLite%5FV2&FolderCTID=0x0120000760EF0E9D65B249BB00FD8C55A72E1B&View=%7BA4ACADA0%2D4A0A%2D47E6%2D8D6F%2D71FEB1C552CB%7D
Description | FW release for Hendrix Lite
Release Package | 1. BT [Contains Bluetooth module image] 2. MCU [Contains mcu image] 3. DSP [Contains the DSP design]
Release Contents | 1. MCU Firmware :6.0.5 + ADAU1761 : 0.6 EQ 3.10 + BT QCC3008 : ZoundHendrix_M_FW_201812201739
Major Modifications Included in this release | Changes: ZSR-38 When DUT is streaming in BT mode,DUT enter BT pairing.Press source button without response and LED flash constantly Further observe: ZSR-30 Unknown situation crash,Did not enter standby mode for 10 minutes ZSR-32 When playing music, leaving the Bluetooth range, after 12 hours, the machine crashes, and there is no response when checking the power cord
Special Notes
Bug Fix

## V6.0.4
|  |  | Customer : | Zound
Project Name | Hendrix M Lite V2 | FW TL | Edmond Sung
Version # | 6.0.4 | Release Date | 2021-07-19
CheckSum |  | SHA1-ID
Release Package Path | http://intranet.tymphany.com/Departments/sw/Shared%20Documents/Forms/AllItems.aspx?RootFolder=%2FDepartments%2Fsw%2FShared%20Documents%2FSW%20Releases%2FReleases%2FZound%2FHendrix%5FM%5FLite%5FV2&FolderCTID=0x0120000760EF0E9D65B249BB00FD8C55A72E1B&View=%7BA4ACADA0%2D4A0A%2D47E6%2D8D6F%2D71FEB1C552CB%7D
Description | FW release for Hendrix Lite
Release Package | 1. BT [Contains Bluetooth module image] 2. MCU [Contains mcu image] 3. DSP [Contains the DSP design]
Release Contents | 1. MCU Firmware :6.0.4 + ADAU1761 : 0.6 EQ 3.10 + BT QCC3008 : ZoundHendrix_M_FW_201812201739
Major Modifications Included in this release | Changes: ZSR-31 When DUT is in standby mode,BT connect,wake up DUT,Play BT audio,then connect AUX ZSR-30 Unknown situation crash,Did not enter standby mode for 10 minutes ZSR-32 When playing music, leaving the Bluetooth range, after 12 hours, the machine crashes, and there is no response when checking the power cord
Special Notes
Bug Fix

## V6.0.3
|  |  | Customer : | Zound
Project Name | Hendrix_Lite | FW TL | Edmond Sung
Version # | 6.0.3 | Release Date | 2021-07-15
CheckSum |  | SHA1-ID
Release Package Path | http://intranet.tymphany.com/Departments/sw/Shared%20Documents/Forms/AllItems.aspx?RootFolder=%2FDepartments%2Fsw%2FShared%20Documents%2FSW%20Releases%2FReleases%2FZound%2FHendrix%5FM%5FLite%5FV2&FolderCTID=0x0120000760EF0E9D65B249BB00FD8C55A72E1B&View=%7BA4ACADA0%2D4A0A%2D47E6%2D8D6F%2D71FEB1C552CB%7D
Description | FW release for Hendrix Lite
Release Package | 1. BT [Contains Bluetooth module image] 2. MCU [Contains mcu image] 3. DSP [Contains the DSP design]
Release Contents | 1. MCU Firmware :6.0.3 + ADAU1761 : 0.6 EQ 3.10 + BT QCC3008 : ZoundHendrix_M_FW_201812201739
Major Modifications Included in this release | Changes: [ZSR-32] When playing music, leaving the Bluetooth range, after 12 hours, the machine crashes, and there is no response when checking the power cord [ZSR-31] When DUT is in standby mode,BT connect,wake up DUT,Play BT audio,then connect AUX Please observe: [ZSR-30] Unknown situation crash,Did not enter standby mode for 10 minutes
Special Notes
Bug Fix

## 2021-6-14
|  |  | Customer : | Zound
Project Name | Hendrix_Lite | FW TL | Edmond Sung
Version # | 6.0.2 | Release Date | 2021-06-14
CheckSum |  | SHA1-ID
Release Package Path | http://intranet.tymphany.com/Departments/sw/Shared%20Documents/Forms/AllItems.aspx?RootFolder=%2FDepartments%2Fsw%2FShared%20Documents%2FSW%20Releases%2FReleases%2FZound%2FHendrix%5FM%5FLite%5FV2%2F6%2E0%2E2&FolderCTID=0x0120000760EF0E9D65B249BB00FD8C55A72E1B&View=%7BA4ACADA0%2D4A0A%2D47E6%2D8D6F%2D71FEB1C552CB%7D&InitialTabId=Ribbon%2EDocument&VisibilityContext=WSSTabPersistence
Description | FW release for Hendrix Lite
Release Package | 1. BT [Contains Bluetooth module image] 2. MCU [Contains mcu image] 3. DSP [Contains the DSP design]
Release Contents | 1. MCU Firmware :6.0.2 + ADAU1761 : 0.6 EQ 3.10 + BT QCC3008 : ZoundHendrix_M_FW_201812201739
Major Modifications Included in this release | Changes: - Change PTE command baudrate to 38400 Known Issue: Auto-standby power consumption seems high, to be checked by EE.
Special Notes
Bug Fix

## 2018-12-24
|  |  | Customer : | Zound
Project Name | Hendrix_Lite | FW TL | Bill Wu
Version # | 4.0.2 | Release Date | 2019-07-08
CheckSum |  | SHA1-ID
Release Package Path | http://intranet.tymphany.com/Departments/sw/Shared%20Documents/SW%20Releases/Releases/Zound%20Hendrix%20M%20CD/4.0.2
Description | FW release for Hendrix Lite
Release Package | 1. BT [Contains Bluetooth module image] 2. MCU [Contains mcu image] 3. DSP [Contains the DSP design]
Release Contents | 1. MCU Firmware :1.0.0 + ADAU1761 : 0.6 EQ 3.10 + BT QCC3008 : ZoundHendrix_M_FW_201812201739
Major Modifications Included in this release | Changes: 1.Modify battery table
Special Notes
Bug Fix

## 2018-12-13
|  |  | Customer : | Zound
Project Name | Hendrix_M | FW TL | William.Wang
Version # | 5.0.3 | Release Date | 2018-12-13
CheckSum |  | SHA1-ID
Release Package Path | http://intranet.tymphany.com/Departments/sw/Shared%20Documents/SW%20Releases/Releases/Zound%20Hendrix%20M/5.0.3
Description | FW release for Hendrix M
Release Package | 1. BT [Contains Bluetooth module image] 2. MCU [Contains mcu image] 3. DSP [Contains the DSP design]
Release Contents | 1. MCU Firmware : 5.0.3 + ADAU1761 : 0.5 EQ 3.04 + BT QCC3008 : ZoundHendrix_M_FW_V05_201811021739
Major Modifications Included in this release | Changes: 1. MCU update a. Bugfix b. Battery table update
Special Notes
Bug Fix

## 2018-11-21
|  |  | Customer : | Zound
Project Name | Hendrix_M | FW TL | William.Wang
Version # | 5.0.2 | Release Date | 2018-11-21
CheckSum |  | SHA1-ID
Release Package Path | http://intranet.tymphany.com/Departments/sw/Shared%20Documents/SW%20Releases/Releases/Zound%20Hendrix%20M/5.0.2
Description | FW release for Hendrix M
Release Package | 1. BT [Contains Bluetooth module image] 2. MCU [Contains mcu image] 3. DSP [Contains the DSP design]
Release Contents | 1. MCU Firmware : 5.0.2 + ADAU1761 : 0.5 EQ 3.04 + BT QCC3008 : ZoundHendrix_M_FW_V05_201811021739
Major Modifications Included in this release | Changes: 1.BT Update a. Volume step change to 16 2. MCU update b. volume step change to 64
Special Notes
Bug Fix

## 2018-07-16
|  |  | Customer : | Zound
Project Name | Hendrix_M | FW TL | William.Wang
Version # | 5.0.1 | Release Date | 2018-07-16
CheckSum |  | SHA1-ID
Release Package Path | http://intranet.tymphany.com/Departments/sw/Shared%20Documents/SW%20Releases/Releases/Zound%20Hendrix%20M/5.0.1
Description | FW release for Hendrix M
Release Package | 1. BT [Contains Bluetooth module image] 2. MCU [Contains mcu image] 3. DSP [Contains the DSP design]
Release Contents | 1. MCU Firmware : 5.0.1 + ADAU1761 : 0.5 EQ 3.04 + BT QCC3008 : ZoundHendrix_M_FW_201807111739
Major Modifications Included in this release | Changes: 1.BT Update a. Audio cue bugfix 2. MCU update b. Battery capacity caculation method update
Special Notes
Bug Fix

## 2018-07-02
|  |  | Customer : | Zound
Project Name | Hendrix_M | FW TL | William.Wang
Version # | 5.0.0 | Release Date | 2018-07-02
CheckSum |  | SHA1-ID
Release Package Path | http://intranet.tymphany.com/Departments/sw/Shared%20Documents/SW%20Releases/Releases/Zound%20Hendrix%20M/5.0.0
Description | FW release for Hendrix M
Release Package | 1. BT [Contains Bluetooth module image] 2. MCU [Contains mcu image] 3. DSP [Contains the DSP design]
Release Contents | 1. MCU Firmware : 5.0.0 + ADAU1761 : 0.5 EQ 3.04 + BT QCC3008 : ZoundHendrix_M_FW_201806271739
Major Modifications Included in this release | Changes: 1.BT disabled battery indicator 2.Updated UI as customer a. factory reset LED pulse once only b. low battery notification before 1 hour power off & every 30min c. battery capacity caculation d. removed 5% 10% battery capacity LED indication
Special Notes
Bug Fix

## 2018-06-11
|  |  | Customer : | Zound
Project Name | Hendrix_M | FW TL | William.Wang
Version # | 4.0.5 | Release Date | 2018-06-11
CheckSum |  | SHA1-ID | 159c48530151149719861a4829672dd3b7848a49
Release Package Path | http://intranet.tymphany.com/Departments/sw/Shared%20Documents/SW%20Releases/Releases/Zound%20Hendrix%20M/4.0.5
Description | FW release for Hendrix M
Release Package | 1. BT [Contains Bluetooth module image] 2. MCU [Contains mcu image] 3. DSP [Contains the DSP design]
Release Contents | 1. MCU Firmware : 4.0.5 + ADAU1761 : 0.5 EQ 3.04 + BT QCC3008 : ZoundHendrix_M_FW_201805071639
Major Modifications Included in this release | Changes: 1.Bugfix Boost control.
Special Notes | 1. Known issue: a. Battery led display will be influenced by power consume & Charging status
Bug Fix

## 2018-06-01
|  |  | Customer : | Zound
Project Name | Hendrix_M | FW TL | William.Wang
Version # | 4.0.4 | Release Date | 2018-06-01
CheckSum |  | SHA1-ID | 159c48530151149719861a4829672dd3b7848a49
Release Package Path | http://intranet.tymphany.com/Departments/sw/Shared%20Documents/SW%20Releases/Releases/Zound%20Hendrix%20M/4.0.4
Description | FW release for Hendrix M
Release Package | 1. BT [Contains Bluetooth module image] 2. MCU [Contains mcu image] 3. DSP [Contains the DSP design]
Release Contents | 1. MCU Firmware : 4.0.4 + ADAU1761 : 0.5 EQ 3.04 + BT QCC3008 : ZoundHendrix_M_FW_201805071639
Major Modifications Included in this release | Changes: 1.Added auto boost control
Special Notes | 1. Known issue: a. Battery led display will be influenced by power consume & Charging status
Bug Fix

## 2018-05-28
|  |  | Customer : | Zound
Project Name | Hendrix_M | FW TL | William.Wang
Version # | 4.0.3 | Release Date | 2018-05-29
CheckSum |  | SHA1-ID | eb767986799e79f3400f0230c847a0d613069577
Release Package Path | http://intranet.tymphany.com/Departments/sw/Shared%20Documents/SW%20Releases/Releases/Zound%20Hendrix%20M/4.0.3
Description | FW release for Hendrix M
Release Package | 1. BT [Contains Bluetooth module image] 2. MCU [Contains mcu image] 3. DSP [Contains the DSP design]
Release Contents | 1. MCU Firmware : 4.0.3 + ADAU1761 : 0.5 EQ 3.04 + BT QCC3008 : ZoundHendrix_M_FW_201805071639
Major Modifications Included in this release | Changes: 1.Updated UI Requsted by Customer
Special Notes | 1. Known issue: a. Battery led display will be influenced by power consume & Charging status
Bug Fix

## 2018-05-21
|  |  | Customer : | Zound
Project Name | Hendrix_M | FW TL | William.Wang
Version # | 4.0.2 | Release Date | 2018-05-21
CheckSum |  | SHA1-ID | 9da88d8f99f6feb46a51e7bef483598e3421198f
Release Package Path | http://intranet.tymphany.com/Departments/sw/Shared%20Documents/SW%20Releases/Releases/Zound%20Hendrix%20M/4.0.2
Description | FW release for Hendrix M
Release Package | 1. BT [Contains Bluetooth module image] 2. MCU [Contains mcu image] 3. DSP [Contains the DSP design]
Release Contents | 1. MCU Firmware : 4.0.2 + ADAU1761 : 0.5 EQ 3.04 + BT QCC3008 : ZoundHendrix_M_FW_201805071639
Major Modifications Included in this release | Changes: 1.Updated DSP
Special Notes | 1. Known issue: a. Battery led display will be influenced by power consume & Charging status
Bug Fix

## 2018-05-11
|  |  | Customer : | Zound
Project Name | Hendrix_M | FW TL | William.Wang
Version # | 4.0.1 | Release Date | 2018-05-11
CheckSum |  | SHA1-ID | 92aac2851500dc4e53be8a4f7ad06baea80b60d2
Release Package Path | http://intranet.tymphany.com/Departments/sw/Shared%20Documents/SW%20Releases/Releases/Zound%20Hendrix%20M/4.0.1
Description | FW release for Hendrix M
Release Package | 1. BT [Contains Bluetooth module image] 2. MCU [Contains mcu image] 3. DSP [Contains the DSP design]
Release Contents | 1. MCU Firmware : 4.0.1 + ADAU1761 : 0.5 EQ 3.02 + BT QCC3008 : ZoundHendrix_M_FW_201805071639
Major Modifications Included in this release | Changes: 1.Updated MCU Firmware a. improved system stablilty b. improved led indication c. changed low battery protect logic
Special Notes | 1. Known issue: a. Battery led display will be influenced by power consume & Charging status
Bug Fix

## 2018-05-09
|  |  | Customer : | Zound
Project Name | Hendrix_M | FW TL | William.Wang
Version # | 4.0.0 | Release Date | 2018-05-09
CheckSum |  | SHA1-ID | 090bf9a20c60b2f0e5052551f03172959d453a8d
Release Package Path | http://intranet.tymphany.com/Departments/sw/Shared%20Documents/SW%20Releases/Releases/Zound%20Hendrix%20M/4.0.0
Description | FW release for Hendrix M
Release Package | 1. BT [Contains Bluetooth module image] 2. MCU [Contains mcu image] 3. DSP [Contains the DSP design]
Release Contents | 1. MCU Firmware : 4.0.0 + ADAU1761 : 0.5 EQ 3.02 + BT QCC3008 : ZoundHendrix_M_FW_201805071639
Major Modifications Included in this release | Changes: 1.Update BT Firmware a. audio cue bugfix b. increase command stability 2.Updated MCU Firmware a. Added LS Sample mode b. improved led indication c. decreased powering up voltage threshold to 5% 3. Updated DSP a. Customer provided EQ
Special Notes | 1. Known issue: a. Battery led display will be influenced by power consume & Charging status
Bug Fix

## 2018-04-25
|  |  | Customer : | Zound
Project Name | Hendrix_M | FW TL | William.Wang
Version # | 3.0.5 | Release Date | 2018-04-26
CheckSum |  | SHA1-ID | 32e828c23d427e4f0f8d2881027e515ae95d2bce
Release Package Path | http://intranet.tymphany.com/Departments/sw/Shared%20Documents/SW%20Releases/Releases/Zound%20Hendrix%20M/3.0.5
Description | FW release for Hendrix M
Release Package | 1. BT [Contains Bluetooth module image] 2. MCU [Contains mcu image] 3. DSP [Contains the DSP design]
Release Contents | 1. MCU Firmware : 3.0.5 + ADAU1761 : 0.5 EQ 3.01 + BT QCC3008 : ZoundHendrix_M_FW_201804251139
Major Modifications Included in this release | Changes: 1.Update BT Firmware b. Improved battery indication 2.Updated MCU Firmware a. source switch 3. Updated DSP
Special Notes | 1. Known issue: a. Battery led display will be influenced by power consume & Charging status
Bug Fix

## 2018-04-20
|  |  | Customer : | Zound
Project Name | Hendrix_M | FW TL | William.Wang
Version # | 3.0.4 | Release Date | 2018-04-20
CheckSum |  | SHA1-ID | d580983a404bbbbae692fd57f0f3a8bb1037db48
Release Package Path | http://intranet.tymphany.com/Departments/sw/Shared%20Documents/SW%20Releases/Releases/Zound%20Hendrix%20M/3.0.4
Description | FW release for Hendrix M
Release Package | 1. BT [Contains Bluetooth module image] 2. MCU [Contains mcu image] 3. DSP [Contains the DSP design]
Release Contents | 1. MCU Firmware : 3.0.4 + ADAU1761 : 0.5 EQ 2.07 + BT QCC3008 : ZoundHendrix_M_FW_201804181139
Major Modifications Included in this release | Changes: 1.Update BT Firmware b. Improved cue performance 2.Updated MCU Firmware a. improved stability b. Improved cue performance c. Reduced cue volume
Special Notes | 1. Known issue: a. Battery led display will be influenced by power consume & Charging status b. Powering up battery limit & off charging limit isn't match.
Bug Fix | cue issues
pos mode volume knob issue
Start up source switch issue
factory reset issue

## 2018-04-17
|  |  | Customer : | Zound
Project Name | Hendrix_M | FW TL | William.Wang
Version # | 3.0.3 | Release Date | 2018-04-17
CheckSum |  | SHA1-ID | 79dd0509ec5027fb2cf35b4b31b513fbed56d69a
Release Package Path | http://intranet.tymphany.com/Departments/sw/Shared%20Documents/SW%20Releases/Releases/Zound%20Hendrix%20M/3.0.3
Description | FW release for Hendrix M
Release Package | Zound_Hendrix_M_hwEVT_swV3.0.3_20180417.zip : 1. BT [Contains Bluetooth module image] 2. MCU [Contains mcu image] 3. DSP [Contains the DSP design]
Release Contents | 1. MCU Firmware : 3.0.3 + ADAU1761 : 0.5 EQ 2.07 + BT QCC3008 : ZoundHendrix_M_FW_201804161139
Major Modifications Included in this release | Changes: 1.Update BT Firmware b. Improved cue performance 2.Updated MCU Firmware a. improved stability
Special Notes | 1. Known issue: a. Battery led display will be influenced by power consume & Charging status b. Powering up battery limit & off charging limit isn't match.
Bug Fix | cue issues

## 2018-04-13
|  |  | Customer : | Zound
Project Name | Hendrix_M | FW TL | William.Wang
Version # | 3.0.2 | Release Date | 2018-04-13
CheckSum |  | SHA1-ID | b12ea47834394f483a9e5092dbac85e3bc0d7efe
Release Package Path | http://intranet.tymphany.com/Departments/sw/Shared%20Documents/SW%20Releases/Releases/Zound%20Hendrix%20M/3.0.2
Description | FW release for Hendrix M
Release Package | Zound_Hendrix_M_hwEVT_swV3.0.2_20180412.zip : 1. BT [Contains Bluetooth module image] 2. MCU [Contains mcu image] 3. DSP [Contains the DSP design]
Release Contents | 1. MCU Firmware : 3.0.2 + ADAU1761 : 0.5 EQ 2.07 + BT QCC3008 : ZoundHendrix_M_FW_201804131139
Major Modifications Included in this release | Changes: 1.Update BT Firmware a. improved reconnect performance b. Improved cue performance c. improved device volume sync 2.Updated MCU Firmware a. improved cue performance
Special Notes | 1. Known issue: a. Battery led display will be influenced by power consume & Charging status b. Powering up battery limit & off charging limit isn't match.
Bug Fix | bt issues
cue issues

## 2018-04-12
|  |  | Customer : | Zound
Project Name | Hendrix_M | FW TL | William.Wang
Version # | 3.0.1 | Release Date | 2018-04-12
CheckSum |  | SHA1-ID | 8eefb8845c05aa94ba81a1320c81d875b38c9450
Release Package Path | http://intranet.tymphany.com/Departments/sw/Shared%20Documents/SW%20Releases/Releases/Zound%20Hendrix%20M/3.0.1
Description | FW release for Hendrix M
Release Package | Zound_Hendrix_M_hwEVT_swV3.0.1_20180411.zip : 1. BT [Contains Bluetooth module image] 2. MCU [Contains mcu image] 3. DSP [Contains the DSP design]
Release Contents | 1. MCU Firmware : 3.0.1 + ADAU1761 : 0.5 EQ 2.07 + BT QCC3008 : ZoundHendrix_M_FW_201804101139
Major Modifications Included in this release | Changes: 1.Update BT Firmware a. improved reconnect performance b. disabled AAC codec c. removed unused cue 2.UI a. change off-charging led to dim patterns
Special Notes | 1. Known issue: a. Battery led display will be influenced by power consume & Charging status b. Powering up battery limit & off charging limit isn't match. C. Continuous Cue sometimes will comes out incompletely
Bug Fix | led issues
cue issues
bt issues

## 2018-04-04
|  |  | Customer : | Zound
Project Name | Hendrix_M | FW TL | William.Wang
Version # | 3.0.0 | Release Date | 2018-04-04
CheckSum |  | SHA1-ID | 09b3955aaa8fd9c55e01cbc2d56fbd70bdc94da7
Release Package Path | http://intranet.tymphany.com/Departments/sw/Shared%20Documents/SW%20Releases/Releases/Zound%20Hendrix%20M/3.0.0
Description | FW release for Hendrix M
Release Package | Zound_Hendrix_M_hwEVT_swV3.0.0_20180404.zip : 1. BT [Contains Bluetooth module image] 2. MCU [Contains mcu image] 3. DSP [Contains the DSP design]
Release Contents | 1. MCU Firmware : 3.0.0 + ADAU1761 : 0.5 EQ 2.07 + BT QCC3008 : ZoundHendrix_M_FW_201804041139
Major Modifications Included in this release | Changes: 1.Update BT Firmware a. add another PIO to execute CMD b. Add little blank for Cue volume change 2.Update DSP a. Updated Aux audio detection design 3. Speed up audio detection
Special Notes | 1. Known issue: a. b. Pairing with second device will comes out 2 connected Cue. c. Battery led display will be influenced by power consume & Charging status d. e. Power level isn't matched between DUT & Phone f. Powering up battery limit & off charging limit isn't match.
Bug Fix | cue volume issues
standby issues

## 2018-03-30
|  |  | Customer : | Zound
Project Name | Hendrix_M | FW TL | William.Wang
Version # | 2.0.9 | Release Date | 2018-03-30
CheckSum |  | SHA1-ID | 11fb0d6629f646d45053a9b8763938215d71f8e8
Release Package Path | http://intranet.tymphany.com/Departments/sw/Shared%20Documents/SW%20Releases/Releases/Zound%20Hendrix%20M/2.0.9
Description | FW release for Hendrix M
Release Package | Zound_Hendrix_M_hwEVT_swV2.0.9_20180330.zip : 1. BT [Contains Bluetooth module image] 2. MCU [Contains mcu image] 3. DSP [Contains the DSP design]
Release Contents | 1. MCU Firmware : 2.0.9 + ADAU1761 : 0.5 EQ 2.05 + BT QCC3008 : ZoundHendrix_M_FW_201803291639_5
Major Modifications Included in this release | Changes: 1.Update BT Firmware a. using SBC format audio cue b. Speed up BT -> AUX audio switch 2.Update DSP 3. Updated UI a. Connect & Connectable has same led indication. Solid Red b. Change Button trigger from Press to Hold
Special Notes | 1. Known issue: a. audio detection limit is adjusted not enough good, Aux detection will be incorrectly triggered sometimes. b. Pairing with second device will comes out 2 connected Cue. c. Battery led display will be influenced by power consume & Charging status d. Bluetooth reset can't work in current HW, that will leds to BT can't powerup sometime. e. Power level isn't matched between DUT & Phone f. Powering up battery limit & off charging limit isn't match.
Bug Fix | Pop noise issues
BT status issues
Audio cue issues
Battery Led indication issues.
POS mode issues

## 2018-03-16
|  |  | Customer : | Zound
Project Name | Hendrix_M | FW TL | William.Wang
Version # | 2.0.8 | Release Date | 2018-03-16
CheckSum |  | SHA1-ID | 6586beeada111068bd846bea3acf6ee46495b193
Release Package Path | http://intranet.tymphany.com/Departments/sw/Shared%20Documents/Forms/AllItems.aspx?RootFolder=%2FDepartments%2Fsw%2FShared%20Documents%2FSW%20Releases%2FReleases%2FZound%20Hendrix%20M%2F2%2E0%2E8&FolderCTID=0x0120000760EF0E9D65B249BB00FD8C55A72E1B&View=%7BA4ACADA0-4A0A-47E6-8D6F-71FEB1C552CB%7D&InitialTabId=Ribbon%2EDocument&VisibilityContext=WSSTabPersistence
Description | FW release for Hendrix M
Release Package | Zound_Hendrix_M_hwEVT_swV2.0.8_20180316.zip : 1. BT [Contains Bluetooch module image] 2. MCU [Contains mcu image] 3. DSP [Contains the DSP design]
Release Contents | 1. MCU Firmware : 2.0.8 + ADAU1761 : 0.5 + BT QCC3008 : ZoundHendrix_M_FW_201803151639
Major Modifications Included in this release | Changes: 1.Update BT Firmware 2.Update DSP 3. Removed powering up & down cue 4. Updated volume curve 5. Updated UI
Special Notes | 1. Known issue: a. audio detection is adjusted not enough good, too small aux signal will not trigger audio detection. b. System will not warning user that system is too hot. c. Audio Cue will comes out with BT streaming d. Battery led display will be influenced by power consume e. f. g. Bluetooth reset can't work, that will leds to BT can't powerup sometime.
Bug Fix | Critical hot or cold now will let system to sleep
DUT start with connectable BT
POS mode no sound
Battery cannot be fully charged in active
Now in connectable status DUT will slow flash BT led.

## 2018-03-09
|  |  | Customer : | Zound
Project Name | Hendrix_M | FW TL | William.Wang
Version # | 2.0.7 | Release Date | 2018-03-09
CheckSum |  | SHA1-ID | c132575052611c32efc84c15ced6386549acaf5e
Release Package Path | http://intranet.tymphany.com/Departments/sw/Shared%20Documents/Forms/AllItems.aspx?RootFolder=%2FDepartments%2Fsw%2FShared%20Documents%2FSW%20Releases%2FReleases%2FZound%20Hendrix%20M%2F2%2E0%2E7&FolderCTID=0x0120000760EF0E9D65B249BB00FD8C55A72E1B&View=%7BA4ACADA0%2D4A0A%2D47E6%2D8D6F%2D71FEB1C552CB%7D
Description | FW release for Hendrix M
Release Package | Zound_Hendrix_M_hwEVT_swV2.0.7_20180309.zip : 1. BT [Contains Bluetooch module image] 2. MCU [Contains mcu image] 3. DSP [Contains the DSP design]
Release Contents | 1. MCU Firmware : 2.0.7 + ADAU1761 : 0.5 + BT QCC3008 : ZoundHendrix_M_FW_201802271040
Major Modifications Included in this release | Changes: 1.Update BT Firmware 2. Added Reconnect CMD & Disconnect CMD for BT 3. Update UI 4. Update Volume setting & Knob Setting
Special Notes | 1. Known issue: a. Auxin source will hijack BT playback b. Audio Cue not correct everytime c. Audio Cue in BT streaming status almost could not be heard d. Battery led display will be influenced by power consume e. Aux music will comes out while BT powering up f. DUT will enter pairing mode while powering up sometimes. g. Bluetooth reset can't work, that will leds to BT can't powerup sometime.
Bug Fix | fixbug: cann't change source to bt
fixbug:only DC can't powering DUT up
DUT will emit power on audio cue while press BT button in Standy-mode
Battery cannot be fully charged.

## 2018-02-27
|  |  | Customer : | Zound
Project Name | Hendrix_M | FW TL | William.Wang
Version # | 2.0.6 | Release Date | 2018-02-27
CheckSum |  | SHA1-ID | 13df0e209492d325199d91708e3673fd258538f4
Release Package Path | http://intranet.tymphany.com/Departments/sw/Shared%20Documents/Forms/AllItems.aspx?RootFolder=%2FDepartments%2Fsw%2FShared%20Documents%2FSW%20Releases%2FReleases%2FZound%20Hendrix%20M%2F2%2E0%2E6&FolderCTID=0x0120000760EF0E9D65B249BB00FD8C55A72E1B&View=%7BA4ACADA0-4A0A-47E6-8D6F-71FEB1C552CB%7D&InitialTabId=Ribbon%2EDocument&VisibilityContext=WSSTabPersistence
Description | FW release for Hendrix M
Release Package | Zound_Hendrix_M_hwEVT_swV2.0.6_20180227.zip : 1. BT [Contains Bluetooch module image] 2. MCU [Contains mcu image] 3. DSP [Contains the DSP design]
Release Contents | 1. MCU Firmware : 2.0.6 + ADAU1761 : 0.5 + BT QCC3008 : ZoundHendrix_M_FW_201802071639
Major Modifications Included in this release | Changes: 1.Update New DSP with New EQ
Special Notes | 1. Known issue: a. Auxin source hijack can't pause BT playback b. Reconnect function is not ready.
Bug Fix

## 2018-02-09
|  |  | Customer : | Zound
Project Name | Hendrix_M | FW TL | William.Wang
Version # | 2.0.5 | Release Date | 2018-02-09
CheckSum |  | SHA1-ID | 904e209f24e0ffd2bdec2177c2d847a0376b70e8
Release Package Path | http://intranet.tymphany.com/Departments/sw/Shared%20Documents/Forms/AllItems.aspx?RootFolder=%2FDepartments%2Fsw%2FShared%20Documents%2FSW%20Releases%2FReleases%2FZound%20Hendrix%20M&View=%7BA4ACADA0-4A0A-47E6-8D6F-71FEB1C552CB%7D
Description | FW release for Hendrix M
Release Package | Zound_Hendrix_M_hwEVT_swV2.0.5_20180209.zip : 1. BT [Contains Bluetooch module image] 2. MCU [Contains mcu image] 3. DSP [Contains the DSP design]
Release Contents | 1. MCU Firmware : 2.0.5 + ADAU1761 : 0.5 + BT QCC3008 : ZoundHendrix_M_FW_201802071639
Major Modifications Included in this release | Changes: 1.Fixbug : Turn off switch can't shut down system power
Special Notes | 1. Known issue: a. Auxin source hijack can't pause BT playback b. Reconnect function is not ready. C.
Bug Fix
Bugs in SpiraTeam

## 2018-02-08
|  |  | Customer : | Zound
Project Name | Hendrix_M | FW TL | William.Wang
Version # | 2.0.4 | Release Date | 2018-02-08
CheckSum |  | SHA1-ID | 9e5db206b9de3bbb3def5809cdcc500108f6238a
Release Package Path | http://intranet.tymphany.com/Departments/sw/Shared%20Documents/Forms/AllItems.aspx?RootFolder=%2FDepartments%2Fsw%2FShared%20Documents%2FSW%20Releases%2FReleases%2FZound%20Hendrix%20M%2F2%2E0%2E4&FolderCTID=0x0120000760EF0E9D65B249BB00FD8C55A72E1B&View=%7BA4ACADA0-4A0A-47E6-8D6F-71FEB1C552CB%7D&InitialTabId=Ribbon%2EDocument&VisibilityContext=WSSTabPersistence
Description | FW release for Hendrix M
Release Package | Zound_Hendrix_M_hwEVT_swV2.0.4_20180208.zip : 1. BT [Contains Bluetooch module image] 2. MCU [Contains mcu image] 3. DSP [Contains the DSP design]
Release Contents | 1. MCU Firmware : 2.0.4 + ADAU1761 : 0.5 + BT QCC3008 : ZoundHendrix_M_FW_201802071639
Major Modifications Included in this release | Changes: 1.Sleep mode power saving 2. Add reset bt operation while BT powering up 3. Change Cue volume to 8 4. Add battery status Cue 5. Fit new BT firmware 6. Update DSP to 0.5 7. Reduced stay-in-off time to 10s 8. Add channel switch debounce
Special Notes | 1. Known issue: a. Auxin source hijack can't pause BT playback b. Reconnect function is not ready. C.
Bug Fix | DUT goes to semi-active when pairing[IN:013525]
Bugs in SpiraTeam

## 2018-02-03
|  |  | Customer : | Zound
Project Name | Hendrix_M | FW TL | William.Wang
Version # | 2.0.3 | Release Date | 2018-02-03
CheckSum |  | SHA1-ID | b75148548581486b790f74da8518786805d3a364
Release Package Path | http://intranet.tymphany.com/Departments/sw/Shared%20Documents/Forms/AllItems.aspx?RootFolder=%2FDepartments%2Fsw%2FShared%20Documents%2FSW%20Releases%2FReleases%2FZound%20Hendrix%20M%2F2%2E0%2E3&FolderCTID=0x0120000760EF0E9D65B249BB00FD8C55A72E1B&View=%7BA4ACADA0-4A0A-47E6-8D6F-71FEB1C552CB%7D&InitialTabId=Ribbon%2EDocument&VisibilityContext=WSSTabPersistence
Description | FW release for Hendrix M
Release Package | Zound_Hendrix_M_hwEVT_swV2.0.3_20180203.zip : 1. BT [Contains Bluetooch module image] 2. MCU [Contains mcu image] 3. DSP [Contains the DSP design]
Release Contents | 1. MCU Firmware : 2.0.3 + ADAU1761 : 0.4 + BT QCC3008 : ZoundHendrix_M_FW_201801291639
Major Modifications Included in this release | Changes: 1.Fix Sleep Mode Assert 2.Fix Sleep Mode Switch Error
Special Notes | 1. Known issue: a. Auxin source hijack can't pause BT playback b. Reconnect function is not support by current BT firmware. C.
Bug Fix | Fix the bug of Sleep Mode Assert
Fix Sleep Mode Switch Error

## 2018-02-02
|  |  | Customer : | Zound
Project Name | Hendrix_M | FW TL | William.Wang
Version # | 2.0.2 | Release Date | 2018-02-02
CheckSum |  | SHA1-ID | b75148548581486b790f74da8518786805d3a364
Release Package Path | http://intranet.tymphany.com/Departments/sw/Shared%20Documents/Forms/AllItems.aspx?RootFolder=%2FDepartments%2Fsw%2FShared%20Documents%2FSW%20Releases%2FReleases%2FZound%20Hendrix%20M%2F2%2E0%2E2&FolderCTID=0x0120000760EF0E9D65B249BB00FD8C55A72E1B&View=%7BA4ACADA0-4A0A-47E6-8D6F-71FEB1C552CB%7D&InitialTabId=Ribbon%2EDocument&VisibilityContext=WSSTabPersistence
Description | FW release for Hendrix M
Release Package | Zound_Hendrix_M_hwEVT_swV2.0.2_20180202.zip : 1. BT [Contains Bluetooch module image] 2. MCU [Contains mcu image] 3. DSP [Contains the DSP design]
Release Contents | 1. MCU Firmware : 2.0.2 + ADAU1761 : 0.4 + BT QCC3008 : ZoundHendrix_M_FW_201801291639
Major Modifications Included in this release | Changes: 1.Auido souce hijack function 2.Updated Battery indication 3.Changed io setting in sleep mode to saving power 4.Added DSP channel mute command 5.Modified BT setting to improve power cycle performance
Special Notes | 1. Known issue: a. Auxin source hijack can't pause BT playback b. Reconnect function is not support by current BT firmware. C.
Bug Fix | Bugfix: Audio cue comes twice when exit pairing
Bugfix: led still on when NTC leds to sleep,
Close led earlier while into sleep
Bugfix: Audio cue comes twice when pairing[IN:013490]
Bugfix：LP bt button will go to pairing when in aux[IN:013482]
Bugfix: Pause bt for 3s will comes out audio cue
Bugfix: Factory reset error
Bugfix: Charging status can't change while charger plug or unplug
Bugfix: Can't heard poweroff audio cue
….in spirateam.

## 2018-01-23
|  |  | Customer : | Zound
Project Name | Hendrix_M | FW TL | William.Wang
Version # | 2.0.1 | Release Date | 2018-01-23
CheckSum
Release Package Path | http://intranet.tymphany.com/Departments/sw/Shared%20Documents/Forms/AllItems.aspx?RootFolder=%2FDepartments%2Fsw%2FShared%20Documents%2FSW%20Releases%2FReleases%2FZound%20Hendrix%20M%2F2%2E0%2E1&FolderCTID=0x0120000760EF0E9D65B249BB00FD8C55A72E1B&View=%7BA4ACADA0-4A0A-47E6-8D6F-71FEB1C552CB%7D&InitialTabId=Ribbon%2EDocument&VisibilityContext=WSSTabPersistence
Description | FW release for Hendrix M
Release Package | Zound_Hendrix_M_hwEVT_swV2.0.1_20180123.zip : 1. BT [Contains Bluetooch module image] 2. MCU [Contains mcu image] 3. DSP [Contains the DSP design]
Release Contents | 1. MCU Firmware : 2.0.1 + ADAU1761 : 0.3 + BT QCC3008 : ZoundHendrix_M_FW_201801191639
Major Modifications Included in this release | EVT Build firmeware swv2.0.1 is based on swv2.0.0 1. faster led fading 2. update DSP 3. update bluetooth communication protocal 4. update battery charging led pattern 5. add test cmd for PTE & SAE 6. amp init with mute status 7. change volume curve to default
Special Notes | 1. Known issue: a. Audio Cue sound level is too low b. volume level of 0 - 10 is not adjusted
Bug Fix

## 2018-01-12
|  |  | Customer : | Zound
Project Name | Hendrix_M | FW TL | William.Wang
Version # | 2.0.0 | Release Date | 2018-01-12
CheckSum
Release Package Path | http://intranet.tymphany.com/Departments/sw/Shared%20Documents/Forms/AllItems.aspx?RootFolder=%2FDepartments%2Fsw%2FShared%20Documents%2FSW%20Releases%2FReleases%2FZound%20Hendrix%20M%2F2%2E0%2E0&FolderCTID=0x0120000760EF0E9D65B249BB00FD8C55A72E1B&View=%7BA4ACADA0-4A0A-47E6-8D6F-71FEB1C552CB%7D&InitialTabId=Ribbon%2EDocument&VisibilityContext=WSSTabPersistence
Description | FW release for Hendrix M
Release Package | Zound_Hendrix_M_hwEVT_swV2.0.0_20180112.zip : 1. BT [Contains Bluetooch module image] 2. MCU [Contains mcu image] 3. DSP [Contains the DSP design]
Release Contents | 1. MCU Firmware : 2.0.0 + ADAU1761 : 0.3 + BT QCC3008 : 201801121430
Major Modifications Included in this release | 1. EVT PCBA bring up a.Common function ready(power circle,audio,led display,button operation) b.Treble & Bass turning function, c.Music detection function, d.PTE test command, e.Standby & Sleep function, BT key&vol knob&DC-in wakeup f.Battery charging g.NTC behavior
Special Notes | 1. Known issue: a. bt sometimes can't start up b. can't exit pairing c. enter pairing function not stable d. audio cue volume issue e. charging battery indication not updated f. volume step not very smooth
Bug Fix

## 2017-12-07
|  |  | Customer : | Zound
Project Name | Hendrix_M | FW TL | William.Wang
Version # | 1.0.1 | Release Date | 2017-12-07
CheckSum
Release Package Path | http://intranet.tymphany.com/Departments/sw/Shared%20Documents/Forms/AllItems.aspx?RootFolder=%2FDepartments%2Fsw%2FShared%20Documents%2FSW%20Releases%2FReleases%2FZound%20Henrix%20M%2FZound_Hendrix_M_hwES_swV1%2E0%2E1_20171207&FolderCTID=0x0120000760EF0E9D65B249BB00FD8C55A72E1B&View=%7BA4ACADA0-4A0A-47E6-8D6F-71FEB1C552CB%7D&InitialTabId=Ribbon%2EDocument&VisibilityContext=WSSTabPersistence
Description | FW release for Hendrix M
Release Package | Zound_Hendrix_M_hwES_swV1.0.1_20171207.zip : 1. BT [Contains Bluetooch module image] 2. MCU [Contains mcu image] 3. DSP [Contains the DSP design]
Release Contents | 1. MCU Firmware : 1.0.1 + ADAU1761 : 0.11 + BT QCC3008 : 201711201639
Major Modifications Included in this release | 1. New code base & based on ES1, pre-EVT release, a. aux in music b. bt music c. RGB led indication d. Battery led indication e. Volume adjust f. Source switch(press multi button to switch source, led indication: blue :bt ;white :AUX) g. Knob & key response (through TP monitor) i. charge in
Special Notes | Do not test function : Special tips : Source swtich bug, powering down bug, sleep mode bug, No battery level & NTC function support No music detection & treble & bass function support
Bug Fix

## 2017-11-02
|  |  | Customer : | Zound
Project Name | Hendrix_M | FW TL | William.Wang
Version # | 1.0.0 | Release Date | 2017-11-02
CheckSum
Release Package Path | http://intranet.tymphany.com/Departments/sw/Shared%20Documents/Forms/AllItems.aspx?RootFolder=%2FDepartments%2Fsw%2FShared%20Documents%2FSW%20Releases%2FReleases%2FZound%20Henrix%20M&FolderCTID=0x0120000760EF0E9D65B249BB00FD8C55A72E1B&View=%7BA4ACADA0-4A0A-47E6-8D6F-71FEB1C552CB%7D&InitialTabId=Ribbon%2EDocument&VisibilityContext=WSSTabPersistence
Description | FW release for Hendrix M
Release Package | Zound_Hendrix_M_hwES_swV1.0.0_20171102.zip : 1. BT [Contains Bluetooch module image] 2. MCU [Contains mcu image] 3. DSP [Contains the DSP design]
Release Contents | 1. MCU Firmware : 1.0.0 + ADAU1761 : 0.1 + BT QCC3008 : 201710311819
Major Modifications Included in this release | 1. PCBA bring up, a. aux in music b. bt music (press bt button to pairing) c. RGB led indication d. Battery led indication (use middle knob to control led) e. Volume adjust f. Source switch(press multi button to switch source, led indication: blue :bt ;white :AUX) g. Knob & key response h. charge out i. charge in
Special Notes | Do not test function : Special tips : Aux in music may contain large noise, please be careful. Charge in function need to adjust charge current at next level, please use external power source
Bug Fix